## SEO 작업일지
SEO 작업일지 |  | https://eclogin.cafe24.com/Shop/ | 로그인정보 : ID : sleepnomad PW : triplehm2022
담당자 : 엄태영 M
날짜 | 작업사이트 | 내용 | 상세 | 엔진 | 작업자
2022-10-24 | 슬리피캣 | 구글서치콘솔 연결 | 서치콘솔 xodud2972.triplehm@gmail.com 에 연결 | 구글 | 엄태영
2022-10-24 | 슬리피캣 | 사이트맵/ RSS생성 | 사이트맵/ RSS생성 | 구글 | 엄태영
2022-10-25 | 슬리피캣 | 색인 생성요청 | 색인이 생성되지 않은 페이지83개 중 8개 요청완료 | 구글 | 엄태영
2022-10-25 | 슬리피캣 | 사이트맵 / RSS 추가 | 사이트맵 / RSS 추가 | 구글 | 엄태영
2022-10-26 | 슬리피캣 | 리디렉션 및 404페이지 색인삭제 요청 | 구 URL 페이지 7개 삭제요청 완료 | 구글 | 엄태영
2022-10-26 | 슬리피캣 | 색인 생성요청 | 색인이 생성되지 않은 페이지83개 중 20개 요청완료 | 구글 | 엄태영
2022-10-27 | 슬리피캣 | 색인 생성요청 | 색인이 생성되지 않은 페이지83개 중 30개 요청완료 | 구글 | 엄태영
2022-10-31 | 슬리피캣 | 색인 생성요청 | 색인이 생성되지 않은 페이지55개 중 10개 요청완료 | 구글 | 엄태영
2022-11-01 | 슬리피캣 | 색인 생성요청 | 색인이 생성되지 않은 페이지55개 중 20개 요청완료 | 구글 | 엄태영
2022-11-02 | 슬리피캣 | 색인 생성요청 | 색인이 생성되지 않은 페이지55개 중 30개 요청완료 | 구글 | 엄태영
2022-11-02 | 슬리피캣 | 색인이 생성되지 않는 사례 파악 | 우측 이미지 | 구글 | 엄태영
2022-11-03 | 슬리피캣 | 색인 생성요청 | 색인이 생성되지 않은 페이지53개 중 40개 요청완료 | 구글 | 엄태영
2022-11-03 | 슬리피캣 | ㄴ | 색인요청1개인데 메인 URL만 색인이 요청된 상태 | 구글 | 엄태영
2022-11-04 | 슬리피캣 | 색인 생성요청 | 색인이 생성되지 않은 페이지53개 중 50개 요청완료 | 구글 | 엄태영
2022-11-04 | 슬리피캣 | 리다렉션오류 28 / 리다렉션포함 페이지 4 | 404페이지3개 / 생인생성되지 않은 페이지 53개 | 구글 | 엄태영
2022-11-07 | 슬리피캣 | 상태 변경 | 색인 생성되지 않은 페이지 모두 리다렉션 오류로 확인 | 구글 | 엄태영
2022-11-07 | 슬리피캣 | 리다렉션 오류 원인 및 사례 수집 | 우측이미지 | 구글 | 엄태영
2022-11-08 | 슬리피캣 | 카페24 SEO 설정내용 검토 | 상품->상품목록->상품별 SEO내역 확인 | 구글 | 엄태영
2022-11-08 | 슬리피캣 | ㄴ | gif파일을 제거하고 jpg를 wepp파일로 변경이 필요 | 구글 | 엄태영
2022-11-08 | 슬리피캣 | 카페24 애널리틱스 내용검토 | 카페24 제공 메뉴 (통계) 확인 | 구글 | 엄태영
2022-11-09 | 슬리피캣 | Lighthouse 내용 검토 | gif파일 및 모든 jpg 사이즈 및 파일크기 절약가능 | 구글 | 엄태영
2022-11-09 | 슬리피캣 | ㄴ | Lighthouse 대부분 이미지 관련 내용(alt속성, width,height) | 구글 | 엄태영
2022-11-10 | 슬리피캣 | stiemap, rss검토 | URL은 정상적으로 확인, 등록도 정상적으로 등록 | 구글 | 엄태영
2022-11-10 | 슬리피캣 | ㄴ | sitemap, rss에 모든 URL이 리다렉션 오류로 확인 | 구글 | 엄태영
2022-11-11 | 슬리피캣 | 10/10~11~10 한달 실적 검토 | 실적 그래프 및 검색어 확인 | 구글 | 엄태영
2022-11-11 | 슬리피캣 | ㄴ | 색인이 되지 않아 실적의 영향에 큰 변화가 없음 | 구글 | 엄태영
2022-11-14 | 슬리피캣 | 색인이 생성되었던 구 URL 검토 | URL을 변경하여 색인을 재요청해볼 것 | 구글 | 엄태영
2022-11-14 | 슬리피캣 | ㄴ | 한글제외 ex) www.sleepycat.co.kr/goods/goods_view.php?goodsNo=1000000157 | 구글 | 엄태영
2022-11-15 | 슬리피캣 | 내용 정리 | 내용정리 시트에 현재까지 내용을 모두 정리 | 구글 | 엄태영 | 리다렉션 오류 원인 및 사례
2022-11-16 | 슬리피캣 | 색인생성 페이지 확인 | 색인이 새로 생성된 3개의 페이지 내용 및 이유파악 | 구글 | 엄태영 | 1. 리디렉션 체인이 너무 김
2022-11-17 | 슬리피캣 | 색인생성 페이지 확인 | gif파일 없이 새로운 제품페이지를 등록했을 경우 색인이 생성되었음 | 구글 | 엄태영 | 2. 리디렉션 순환 오류
2022-11-18 | 슬리피캣 | 색인생성 페이지 확인 | 색인생성된 페이지의 경우 Lighthouse에서 이전과 비교해 월등히 좋은 속도를 나타냄 | 구글 | 엄태영 | 3. 리디렉션 URL이 최대 URL 길이를 초과
2022-11-21 | 슬리피캣 | 유효성검사 | 리다렉션 오류 페이지 목록 유효성 검사 재실행 | 구글 | 엄태영 | 4. 리디렉션 체인에 잘못되거나 빈 URL이 있음
2022-11-22 | 슬리피캣 | 모바일 사용 편의성 페이지 | https://sleepycat.co.kr/product/밀키웨이-파자마-커플/105/ 링크가 우수한 페이지에 추가됨 | 구글 | 엄태영 | 의심 : <meta name="viewport" content="width=device-width, initial-scale=1.0"> 태그 여부
2022-11-23 | 슬리피캣 | 분석 | 전체 사용자 중 70%이상이 모바일로 접속 | 구글 | 엄태영
2022-11-24 | 슬리피캣 | 분석 | 잠옷 관련 키워드로 구글에서 노출되지 않으며 슬리피캣 이름과 비슷한 검색시 노출된다 | 구글 | 엄태영

## 내용정리
내용정리
내용
1 | 색인 생성되지 않는 이유는 크게 네가지 ( URL문제, 리다렉션 문제, 메타태그 여부 문제, 이미지 문제)
2 | URL문제는 현재 한글로 되어있는 URL을 고도몰에서 사용했던 구URL과 같이 숫자와 영어로만 구성되도록 수정하고 비교적 간단하게 변경한다.
3 | ex) https://www.sleepycat.co.kr/goods/goods_view.php?goodsNo=1000000157
4 | 리다렉션 문제는 페이지내 이미지가 로드 되는데 많은 시간이 소요되며 파일 확장자를 변환
5 | jpg->wepp로 변경 / gif파일 제거 ( 용량이 너무 커서 로드 되는데 많은 시간이 소요된다. )
6 | 메타 태그 문제는 공통소스에 <meta name="viewport" content="width=device-width, initial-scale=1.0"> 태그 여부를 확인한다.
7 | 모바일웹이나 반응형웹에서 각각의 기기장치를 인식할 때 사용하는 중요한 태그이며 현재 모든 소스에 viewport는 적용되어있지 않다.
8 | 이미지 문제는 모든 이미지에 alt속성과 height과 width 속성을 넣는다.
9 | 상품상세페이지에 들어가는 이미지에는 alt속성과, height속성이 없고, 파일명 또한 변경해줘야한다.
10 | gif 파일 없이 새로 제품페이지를 추가한 경우에는, 색인이 정상적으로 생성되는 것을 확인 할 수있음.

## 술리피캣 색인 생성요청 내역 목록
날짜 | URL
2022-10-25 | https://sleepycat.co.kr/product/구름-모달-트렁크-여성3c/64/
2022-10-25 | https://sleepycat.co.kr/product/굿데이-파자마팬츠-남성3c/83/
2022-10-25 | https://sleepycat.co.kr/product/굿데이-파자마팬츠-여성3c/82/
2022-10-25 | https://sleepycat.co.kr/product/굿데이-파자마팬츠-커플3c/84/
2022-10-25 | https://sleepycat.co.kr/product/그린메모리-파자마-남성/101/
2022-10-25 | https://sleepycat.co.kr/product/그린메모리-파자마-여성/100/
2022-10-25 | https://sleepycat.co.kr/product/그린메모리-파자마-커플/102/
2022-10-25 | https://sleepycat.co.kr/product/그린하이웨이-파자마-남성/92/
2022-10-26 | https://sleepycat.co.kr/product/그린하이웨이-파자마-여성/91/
2022-10-26 | https://sleepycat.co.kr/product/그린하이웨이-파자마-커플/93/
2022-10-26 | https://sleepycat.co.kr/product/대니-스트라이프-파자마-남성/53/
2022-10-26 | https://sleepycat.co.kr/product/대니-스트라이프-파자마-여성/52/
2022-10-26 | https://sleepycat.co.kr/product/대니-스트라이프-파자마-커플/54/
2022-10-26 | https://sleepycat.co.kr/product/딜라잇드림-기모-체크-파자마-남성/72/
2022-10-26 | https://sleepycat.co.kr/product/딜라잇드림-기모-체크-파자마-여성2c/71/
2022-10-26 | https://sleepycat.co.kr/product/딜라잇드림-기모-체크-파자마-커플/73/
2022-10-26 | https://sleepycat.co.kr/product/로지라운드-파자마-남성/107/
2022-10-26 | https://sleepycat.co.kr/product/로지라운드-파자마-여성/106/
2022-10-26 | https://sleepycat.co.kr/product/로지라운드-파자마-커플/108/
2022-10-26 | https://sleepycat.co.kr/product/모던체크-반팔-파자마-여성2c/77/
2022-10-27 | https://sleepycat.co.kr/product/모던-스트라이프-순면-반팔-파자마-남성/35/
2022-10-27 | https://sleepycat.co.kr/product/모던-스트라이프-순면-반팔-파자마-여성3c/34/
2022-10-27 | https://sleepycat.co.kr/product/모던-스트라이프-순면-반팔-파자마-커플/36/
2022-10-27 | https://sleepycat.co.kr/product/모던-체크-파자마-남성/27/
2022-10-27 | https://sleepycat.co.kr/product/모던-체크-파자마-여성2c/28/
2022-10-27 | https://sleepycat.co.kr/product/모던-체크-파자마-커플/29/
2022-10-27 | https://sleepycat.co.kr/product/밀키웨이-파자마-남성/104/
2022-10-27 | https://sleepycat.co.kr/product/밀키웨이-파자마-여성/103/
2022-10-27 | https://sleepycat.co.kr/product/밀키웨이-파자마-커플/105/
2022-10-27 | https://sleepycat.co.kr/product/블러썸-순면-파자마-남성/66/
2022-10-31 | https://sleepycat.co.kr/product/블러썸-순면-파자마-여성/65/
2022-10-31 | https://sleepycat.co.kr/product/블러썸-순면-파자마-커플/67/
2022-10-31 | https://sleepycat.co.kr/product/솔리드-스판-반팔-파자마-여성3c/26/
2022-10-31 | https://sleepycat.co.kr/product/솔리드-스판-파자마-여성5c/24/
2022-10-31 | https://sleepycat.co.kr/product/스노우플레이크-파자마-남성/95/
2022-10-31 | https://sleepycat.co.kr/product/스노우플레이크-파자마-여성/94/
2022-10-31 | https://sleepycat.co.kr/product/스노우플레이크-파자마-커플/96/
2022-10-31 | https://sleepycat.co.kr/product/스몰체크-리플-순면-쇼츠-공용3c/63/
2022-10-31 | https://sleepycat.co.kr/product/스몰체크-리플-순면-팬츠-공용5c/62/
2022-10-31 | https://sleepycat.co.kr/product/스몰-도트-순면-파자마-남성/32/
2022-11-01 | https://sleepycat.co.kr/product/스몰-도트-순면-파자마-여성/31/
2022-11-01 | https://sleepycat.co.kr/product/스몰-도트-순면-파자마-커플/33/
2022-11-01 | https://sleepycat.co.kr/product/스몰-체크-순면-반팔-파자마-남성/38/
2022-11-01 | https://sleepycat.co.kr/product/스몰-체크-순면-반팔-파자마-여성3c/37/
2022-11-01 | https://sleepycat.co.kr/product/스몰-체크-순면-반팔-파자마-커플/39/
2022-11-01 | https://sleepycat.co.kr/product/스몰-체크-순면-파자마-남성/45/
2022-11-01 | https://sleepycat.co.kr/product/스몰-체크-순면-파자마-여성3c/44/
2022-11-01 | https://sleepycat.co.kr/product/스몰-체크-순면-파자마-커플/46/
2022-11-01 | https://sleepycat.co.kr/product/스무디나잇-기모-체크-파자마-남성2c/69/
2022-11-01 | https://sleepycat.co.kr/product/스무디나잇-기모-체크-파자마-여성2c/68/
2022-11-02 | https://sleepycat.co.kr/product/스무디나잇-기모-체크-파자마-커플/70/
2022-11-02 | https://sleepycat.co.kr/product/시에스타-순면-파자마-남성/59/
2022-11-02 | https://sleepycat.co.kr/product/시에스타-순면-파자마-여성/58/
2022-11-02 | https://sleepycat.co.kr/product/시에스타-순면-파자마-커플/60/
2022-11-02 | https://sleepycat.co.kr/product/심플-스판-반팔-파자마-여성/25/
2022-11-02 | https://sleepycat.co.kr/product/씬체크-순면-파자마-남성2c/56/
2022-11-02 | https://sleepycat.co.kr/product/씬체크-순면-파자마-여성2c/55/
2022-11-02 | https://sleepycat.co.kr/product/씬체크-순면-파자마-커플/57/
2022-11-02 | https://sleepycat.co.kr/product/오션-스트라이프-파자마-남성3c/86/
2022-11-02 | https://sleepycat.co.kr/product/오션-스트라이프-파자마-여성3c/85/
2022-11-03 | https://sleepycat.co.kr/product/오션-스트라이프-파자마-커플3c/87/
2022-11-03 | https://sleepycat.co.kr/product/와일드플라워-파자마-남성/98/
2022-11-03 | https://sleepycat.co.kr/product/와일드플라워-파자마-여성/97/
2022-11-03 | https://sleepycat.co.kr/product/와일드플라워-파자마-커플/99/
2022-11-03 | https://sleepycat.co.kr/product/원더라인-파자마-남성/110/
2022-11-03 | https://sleepycat.co.kr/product/원더라인-파자마-여성/109/
2022-11-03 | https://sleepycat.co.kr/product/원더라인-파자마-커플/111/
2022-11-03 | https://sleepycat.co.kr/product/젠-파자마팬츠-남성/113/
2022-11-03 | https://sleepycat.co.kr/product/젠-파자마팬츠-여성/112/
2022-11-03 | https://sleepycat.co.kr/product/젠-파자마팬츠-커플/114/
2022-11-04 | https://sleepycat.co.kr/product/쿨-스트라이프-파자마-쇼츠-남성2c/42/
2022-11-04 | https://sleepycat.co.kr/product/쿨-스트라이프-파자마-쇼츠-여성3c/41/
2022-11-04 | https://sleepycat.co.kr/product/쿨-스트라이프-파자마-쇼츠-커플/43/
2022-11-04 | https://sleepycat.co.kr/product/트윙클-체크-순면-파자마-여성2c/61/
2022-11-04 | https://sleepycat.co.kr/product/파스텔-체크-기모-파자마-남성2c/50/
2022-11-04 | https://sleepycat.co.kr/product/파스텔-체크-기모-파자마-여성2c/49/
2022-11-04 | https://sleepycat.co.kr/product/파스텔-체크-기모-파자마-커플/51/
2022-11-04 | https://sleepycat.co.kr/product/파스텔-포켓-순면-팬츠-남성/48/
2022-11-04 | https://sleepycat.co.kr/product/파스텔-포켓-순면-팬츠-여성2c/47/
2022-11-04 | https://sleepycat.co.kr/product/프라이데이나잇-파자마-남성/89/